## Option 1
Ankeny Regional Airport
Proposed 2025 Airport Capital Improvements Program
December 7, 2023
| Funding | FY 2024 | FY 2025 | FY 2026 | FY 2027
| Federal | 1066500 | 14658417 | 3371400 | 0
| State | 965000 | 350000 | 500000 | 1200000
| Local | 1649500 | 2751063 | 1524600 | 1675000
Project Description | Total | 3681000 | 17759480 | 5396000 | 2875000 | Notes
| Federal | 0 |  |  |  | Entry signs, destination signs, and possibly entry landscape features.
Airport Brand Signing and Entry Improvements | State | 0 |  |  |  | Project design has started at this time.
| Local | 225000 |  |  |  | Construction of signs and features to be completed with
| Total | 225000 |  |  |  | local funds in FY 24. | .
| Federal | 828000 | 13263417 |  |  | McClure completed the Pav't Determination in FY 23.
Reconstruct Runway 18/36 | State | 0 | 0 |  |  | HDR completed the Environmental in FY 23.
Final Design and Construction | Local | 92000 | 1473713 |  |  | Final Design in FY 24. Construction in FY 25.
| Total | 920000 | 14737130 |  |  | Schedule as dictated by FAA.
| Federal | 238500 |  |  |  | Includes a 500' extension of RW 18 to a total of 6,000'.
Extend Runway 18 | State | 0 |  |  |  | Scope includes moving localizer.
Relocate Localizer | Local | 26500 |  |  |  | Advanced design to '24 to match reconstruction design for efficiency.
Design | Total | 265000 |  |  |  | Possible future FAA reimbursable using Entitlement Funds
| Federal | 0 |  |  |  | Single row of box hangars along north property line.
North Property Line Box Hangars - Phase 1 | State | 565000 |  |  |  | Received DOT GAVI Grant and AIP Grant.
| Local | 690000 |  |  |  | Project designed and bid in FY 23. Currently under construction.
| Total | 1255000
| Federal | 0 |  |  |  | Final phase of Taxiway D projects.
Taxiway D Apron and Access Roadway | State | 400000 |  |  |  | Design services funded in FY 2023.
Paving - Phase 4 | Local | 616000 |  |  |  | Received Iowa DOT grant for $400,000 max.
| Total | 1016000
| Federal |  | 530000 |  |  | Replace roundabout and entrance drive to the west.
Remove and Replace Pavement - | State |  | 0 |  |  | BIL/ATP Competitive Grant Application - 95% FAA funding.
Entrance Drive and Roundabout | Local |  | 28000 |  |  | Project will proceed only if grant awarded.
| Total |  | 558000
| Federal |  | 295000 |  |  | Will do project if above entrance drive project receives BIL/ATP grant.
Remove and Replace Pavement - | State |  | 0 |  |  | Repair pavement deterioration.
Terminal Building Parking Lot | Local |  | 255000 |  |  | Utilize the $295,000 BIL annual discretionary funding for
| Total |  | 550000 |  |  | the majority of the project.
| Federal |  | 570000 |  |  | To provide board meeting room with elevator
Terminal Building Elevator/Lobby Addition | State |  | 0 |  |  | for ADA compliance, and to upgrade terminal building access.
| Local |  | 30000 |  |  | BIL/ATP Competitive Grant Application - 95% FAA funding.
| Total |  | 600000 |  |  | Project will proceed only if grant awarded.
| Federal |  | 0 |  |  | Single row of box hangars along north property line.
North Property Line Box Hangars - Phase 2 | State |  | 350000 |  |  | Possible GAVI grant of $300,000 max.
| Local |  | 914350 |  |  | Possible small AIP grant for flatwork, assume $50,000.
| Total |  | 1264350
| Federal |  |  | 0 |  | Schedule to be dictated by continued pav't deterioration.
Rehabilitate Maintenance Building | State |  |  | 0 |  | Completed full-depth patching of center section in 2017.
Parking Lot | Local |  |  | 350000 |  | Consider this project after terminal lot paving.
| Total |  |  | 350000
| Federal |  |  | 0 |  | For storing snow fighting and mowing equipment.
PCAA Maintenance Building | State |  |  | 500000 |  | Opens up 2-3 tee hangars.
| Local |  |  | 600000 |  | Assumed location at south end of Taxiway D or near FSDO Office.
| Total |  |  | 1100000 |  | Assumed 80' by 80' @ $175/sf const. cost.
|  |  |  | 3371400 |  | Includes a 500' extension of RW 18 to a total of 6,000'.
Extend Runway 18 |  |  |  | 0 |  | Scope includes moving localizer.
Relocate Localizer |  |  |  | 374600 |  | Construction schedule depends upon obtaining FAA funding.
Construction |  |  |  | 3746000
| Federal |  | 0 | 0 | 0 | Two 10-unit bays of tee hangars and taxilanes as an initial phase
Phase 1 South Terminal Tee Hangars | State |  |  |  | 850000 | of the South Corporate Terminal Development.
| Local |  | 50000 | 100000 | 1000000 | Possible special Iowa DOT funding for tee hangars, assume 50%.
| Total |  | 50000 | 100000 | 1850000 | Finalize concept in '25, design in '26, construct in '27.
| Federal |  |  | 0 | 0 | Single row of box hangars along north property line.
North Property Line Box Hangars - Phase 3 | State |  |  |  | 350000 | Possible GAVI grant of $300,000 max.
| Local |  |  | 100000 | 675000 | Possible small AIP grant for flatwork, assume $50,000.
| Total |  |  | 100000 | 1025000 | Design in FY 26, Constrtuct in FY 27.
| Funding | FY 2028 | FY 2029 | FY 2030
| Federal | 1980000 | 675000 | 405000
| State | 200000 | 405000 | 405000
| Local | 520000 | 820000 | 1290000
Project Description | Total | 2700000 | 1900000 | 2100000 | Notes
| Federal | 1980000 |  |  | To prepare the overall development for vertical infrastructure.
South Corporate Terminal - | State | 0 |  |  | Overall site grading, etc. after Phase 1 Tee Hangars completed.
Phase 1 Grading, Drainage and Paving Improvements | Local | 220000 |  |  | Environmental clearance is being done with the 18/36 Reconstruction.
| Total | 2200000 |  |  | Placeholder estimate pending preliminary design.
| Federal | 0 |  |  | Only remaining lights that have direct-buried wiring.
Taxiway D and E Lighting Replacement | State | 200000 |  |  | Utilize either state or federal funding.
| Local | 300000 |  |  | Placeholder estimate pending preliminary design.
| Total | 500000
| Federal |  | 675000
Taxiway C Pavement Replacement | State |  | 0 |  | Based on Iowa DOT 2021 Pavement Condition Index - PCI = 48.
| Local |  | 75000 |  | Assumes FAA grant for 90% of the construction costs.
| Total |  | 750000
| Federal |  | 0 |  | Additional site work needed to develop terminal area.
South Corporate Terminal - | State |  | 405000 |  | Need recorded annual ops.
Phase 2 Grading and Drainage | Local |  | 495000 |  | Assumes Iowa DOT grant for 45% of construction costs.
| Total |  | 900000 |  | Placeholder estimate pending preliminary design.
| Federal |  | 0 |  | Large apron area south of Terminal and west of Taxiway C.
Main Apron Pavement Rehabilitation | State |  | 0 |  | Joint and crack sealing, minor patching.
| Local |  | 250000 |  | Schedule dictated by continued deterioration of apron pavement.
| Total |  | 250000
| Federal |  |  | 405000
Future Runway and Taxiway | State |  |  |  | Need based on anticipated deterioration of fixtures over time.
Lighting Upgrades | Local |  |  | 45000 | Placeholder estimate pending preliminary design.
| Total |  |  | 450000
| Federal |  |  | 0 | Balance of site work needed to develop terminal area.
South Corporate Terminal - | State |  |  | 405000 | Need recorded annual ops.
Phase 3 Grading and Drainage | Local |  |  | 495000 | Need environmental clearance.
| Total |  |  | 900000 | 45% DOT and 55% local funding.
Federal
MALSR for Runway 36 | State |  |  |  | MALSR installation must pass a Benefit / Cost Determination.
| Local |  |  | 750000 | Analysis to be included in the ACIP funding.
| Total |  |  | 750000
Projects targeted for FAA Funding Participation
Projects targeted for Iowa DOT Funding Participation
Projects funded with only Local PCAA Funding
Projects possibly funded by special FAA BIL/ATP Grants
Note on D9: Paul Moritz: